## Slide 1: Pakistan Shelter Sector
National Shelter Sector Meeting
18 October 2022 | Islamabad

## Slide 2: Shelter/NFI Sector Working Group
18.10.2022 Agenda
Welcome and Introduction (5Minutes)
Action points from last meeting (5Minutes)
Situation update (5Minutes)
5Ws data and gap analysis (10Minutes)
Pipeline updates (5Minutes)
PDM updates (5 Minutes)
CCCM updates (10Minutes)
Recovery update (5Minutes)
Challenges and gaps – discussion (10Minutes)
AOB

## Slide 3: Sector Working Group:
Website:
  https://sheltercluster.org/response/pakistan-floods-2022
Sector Coord (Atta Ullah)
Sukkur
(IOM) (Deeba Parvez)
Karachi (IOM) Mariam Hyder
Hyderabad (IOM)
(Safia)
Quetta
(IOM)
Hafeezullah Jogezai
IM
TBC
Punjab
(IOM)
Muhammad Ali
Gilgit – Baltistan
(AKDN)
KPK
(IOM)
Najeeb khan
IM (Syed Shahzad Raza Jaffri)
IM (Brian Mcdonald)
Tech (Antoine Barbier)

## Slide 4: Progress on action points
ACTION: IOM and all: registration for common pipeline is closed for now; https://commonpipeline.iom.int/ ,distribution is in progress. IOM to report common pipeline data to UNOCHA on 5Ws tools (Open)
ACTION: Revised UNOCHA Flash Appeal will be shared with the partners. (Done)
ACTION: Volunteers for ORS Data Collection are required. Partners are requested to share the information for Sindh. (survey InProgress )
ACTION: Need active participation from partners for the Shelter Recovery Working Group. (Group is active)
ACTION: Final TORs of Technical/Early Recovery Working Group will be shared. Partners can share any kind of feedback. (Done)
ACTION: Multisectoral Rapid Need Assessment (MSRNA) report will be shared with the partners. (Done)
ACTION: Finalized Shelter/NFI Kits documents will be shared with the partners. (Done)
ACTION: “Compendium of key documents” will be shared with the partners. (Done)
ACTION: Shelter Sector will share the specifications for the winterized tents with the partners. (Pending)

## Slide 5: 2022 FLOODS RESPONSE PLAN(Revised)
Notes: People targeted 29% of the affected 33M

## Slide 6: 2022 FLOODS RESPONSE PLAN(S/NFI)
Notes: Targeted 30% of people in need

## Slide 7: 4 pillars-Revised appeal
Provide household item support and winter assistance: Flood affected families have the basic items required for cold weather and to resume essential daily routines (like cooking and sleeping) in a dignified and appropriate manner. Target 20% of those whose homes were damaged or destroyed.
Provide dignified emergency shelter assistance: Flood affected families can build or improve their shelters (safe, covered living space) to provide at least a minimum level of safety, security, privacy and dignity in displacement sites. Target 30% of those whose homes were damaged or destroyed.
Provide support for dignified emergency shelter repairs and construction at return locations: Support families returning as water recedes and are able to conduct emergency repairs and build resilient shelters to enable return as the waters recede. Target 10% of those whose homes were damaged or destroyed.
Provide support and coordination to the management of Temporary Sites: Ensure dignified conditions and protection for people living in collective settings by improving coordinated access to assistance, services, and safe living environments particularly from Gender-Based Violence (GBV). Target 30% of those residing in camps. This activity will also include DTM.

## Slide 8: Damaged housing stock (16th Oct)
Source: NDMA Monsoon 2022 Daily Situation Report 16th Oct 2022
Notes: Sindh 83%, Baluchistan 10% , FD 41% , PD 59%

## Slide 9: Affected population (16th Oct)
Notes: 33-districts are prioritized out of 84- based on the damages, and displacement , 2-KPK, 2-Punjab, 16-Sindh and 13-Balochistan

## Slide 10: 5W reporting
Two report process – pipeline or non pipeline
5W data quality:
  Ongoing activities
  What is a distribution?
  People reached
  Why getting the reporting right is important
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 11: 5Ws Data Presentation
  Link to consolidated 5Ws;
  https://docs.google.com/spreadsheets/d/1mPTxVhCtW-NHgAFtcScu9ptTKj99Ykm6y5-ObjBQ_DA/edit?usp=sharing
  Link to UNOCHA interactive dashboard
  2022 Monsoon 5W Dashboard | ReliefWeb Response
  Link to NFRCC dashboard
  nfrcc.nitb.gov.pk
Notes: National flood response and coordination center(NFRCC) .link is down, PM refuse to inaugurate
11

## Slide 12: Households Reached per Province
Balochistan
34513
Gilgit Baltistan
448
Khyber Pakhtunkhwa
20056
Punjab
13748
Sindh
105694
20000
40000
60000
80000
100000
PROVINCE | HOUSEHOLDS REACHED
Sindh | 105,694
Balochistan | 34,513
Khyber Pakhtunkhwa | 20,056
Punjab | 13,748
Gilgit Baltistan | 448

## Slide 13
Gap per Province (households)
PROVINCE | GAP
Sindh | 398,765
Balochistan | met
Khyber Pakhtunkhwa | 7,382
Punjab | 4.324
Gilgit Baltistan | met
*GAP is based against the target of 30% of all damaged and destroyed buildings (as per the revised flash appeal)
Balochistan
0
Gilgit Baltistan
0
Khyber Pakhtunkhwa
7382
Punjab
4324
Sindh
398765
Gap (HHs) per Province
0
50000
100000
150000
200000
250000
300000
350000

## Slide 14: Sindh - Households Reached per District
Badin
1398
Dadu
19517
Ghotki
54
Hyderabad
1900
Jacobabad
10074
Jamshoro
2900
Kambar Shahdad Kot
10792
Kashmore
7480
Khairpur
7315
Larkana
250
Malir Karachi
2500
Matiari
620
Mirpur Khas
9237
Naushahro Feroze
605
Sanghar
4292
Shaheed Benazir Abad
3957
Shikarpur
11013
Sukkur
2989
Umer Kot
7951
2500
5000
7500
10000
12500
15000
17500
DISTRICT | HOUSEHOLDS REACHED
Dadu | 19,517
Shikarpur | 11,013
Kambar Shahdad Kot | 10,792
Jacobabad | 10,074
Mirpur Khas | 9,237
Umer Kot | 7,951
Kashmore | 7,480
Khairpur | 7,315
Sanghar | 4,292
Shaheed Benazir Abad | 3,957
Sukkur | 2,989
Jamshoro | 2,900
Malir Karachi | 2,500
Hyderabad | 1,900
Badin | 1,398
Qambar Shahdadkot | 750
Matiari | 620
Naushahro Feroze | 605
Larkana | 250
Ghotki | 54

## Slide 15: Gap per District (hh)
Badin
10287
Dadu
5512
Ghotki
4558
Hyderabad
-638
Jacobabad
13553
Jamshoro
11119
Kambar Shahdad Kot
-10792
Kashmore
28429
Khairpur
28796
Korangi Karachi
2.0
Larkana
67844
Malir Karachi
-2458
Matiari
2896
Mirpur Khas
46316
Naushahro Feroze
29660
Sanghar
-4292
Shaheed Benazir Abad
-3957
Shikarpur
-397
Sujawal
4236
Sukkur
-2989
Thatta
3009
Umer Kot
-7951
Sindh - Gap (HHs) per District
0
10000
20000
30000
40000
50000
60000
DISTRICT | GAP
Larkana | 67,844
Kamber | 65,534
Mirpur Khas | 46,316
SBA | 41,881
Umerkot | 37,742
Naushahro Feroze | 29,660
Khairpur | 28,796
Kashmore | 28,429
Jacobabad | 13,553
Jamshoro | 11,119
Badin | 10,287
Tando Allahyar | 6,550
Dadu | 5,512
Ghotki | 4,558
Sujawal | 4,236
Thatta | 3,009
Matiari | 2,896
*GAP is based against the target of 30% of all damaged and destroyed buildings (as per the revised flash appeal)

## Slide 16
Sindh - Households Reached per Tehsil
0
1000
2000
3000
4000
5000
6000
… work in progress

## Slide 17: Pipeline updates
  The pipeline stock is now replenished with new items (plastic sheets, ropes, repair toolkits, tent poles)
  Limited number of blankets and sleeping mats will arrive in the coming period. Interested partners should submit separate requests for blankets and mats not to delay the release of the other items.
  New guidelines were circulated to the registered pipeline partners on Thursday 13 October 2022.
  90% of the current submissions are not in-line with the guidelines. Therefore, these submissions will be rejected. We kindly encourage partners to read the guidelines very carefully ahead of your submissions.
  Only one submission per partner is allowed. If the partner’s submission was approved, a new request can be submitted once the first distribution is done successfully.
  Two warehouses available for dispatch – 1 in Sukkur and1 in Hyderabad
  Requests to distribute in hard-to-reach areas and under served locations will be prioritized.

## Slide 18: Post Distribution Monitoring Findings from Pipeline
PDM ongoing, 400 households so far
Findings are preliminary
The PDM survey template used is on the SC website for partner if they wish to use/adapt
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 19: Prior to the Distribution
ngo
64%
relative
24%
dont_know
10%
dont_want_to_answer
2%
How did you become aware about the distribtion process?
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 20: During the distribution
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 21: About the Items
0%
20%
40%
60%
80%
100%
% of respondents
Tarpaulins
Kitchen Sets
Emergency Shelter Kits
NFI Kits
91%
97%
73%
72%
7%
3%
23%
28%
2%
0%
3%
0%
Are you using the items?
Yes
occasionally
No
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 22: Quantity and Quality of Items
0%
20%
40%
60%
80%
100%
% of respondents
Tarpaulins
Kitchen Sets
Emergency Shelter Kits
NFI Kits
97%
99%
98%
97%
3%
1%
2%
3%
Are you happy with the quality of the items?
Yes
somewhat
0%
20%
40%
60%
80%
100%
% of respondents
Tarpaulins
Kitchen Sets
Emergency Shelter Kits
NFI Kits
95%
99%
90%
90%
3%
0%
5%
9%
1%
1%
5%
1%
Was the quantity of the items appropriate?
Yes
Somewhat
No
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 23: CCCM Working Group
National Shelter Sector Meeting
18 October 2022 | Islamabad

## Slide 24: Updates
Displacement and inundation analysis
Upcoming CCCM coordination activities
DTM updates

## Slide 25: Sindh Updates
Conditions and approach for CCCM varies greatly between districts
Reliable data on displacement sites (both formal and informal) is a still a big gap
Discussions with district authorities regarding CCCM support have been ongoing, currently focusing on Sukkur hub – (5 out of 10 districts covered to date, 8 in total for Sindh)
Specific requests for support in CCCM have been received from one district (Qambar Shahdadkot), with other districts requesting support with at the village level, to set up temporary sites in closer vicinity to the IDPs areas of origin, to enable returns from the district hubs and allow IDPs to restart livelihoods and access their homes.

## Slide 27: Upcoming Plans
Step 1
CCCM Partner Capacity Mapping
Step 2
Site Identification
Step 3
Site Monitoring

## Slide 28: Partners' Capacity Mapping
https://ee.kobo.iom.int/x/Yzvtu2Bw

## Slide 29: Displacement Sites Identification
https://ee.kobo.iom.int/x/eL20MnB6

## Slide 30: GoP recovery response update
08.10.2022: World Bank => 500 million USD for housing reconstruction in Sindh only.
10.10.2022: Sindh government has formed a housing company.
2022.10.15: Release of the Post-Disaster Needs Assessment (PDNA) of the damages and losses.
Governmental measures for the reconstruction phase expected on 24th October.
06 to 18.11.2022: COP 27 announced to give its Vice presidency to Pakistan Prime Minister.
End of November TBC: donor conference (global appeal for recovery assistance to floods-affected). Date/place yet undetermined
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 31: Shelter & Settlement Recovery Working Group
2022.10.07: Setting up of Shelter & Settlements Recovery Working Group (SSRWG). Weekly meeting.
This week: Finalization of the SSRWG policy paper.
Next Steps: Develop a Shelter Sector technical assistance strategy.
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 32: AoB