## Slide 1: Pakistan Shelter Sector
National Shelter Sector Meeting
15 November 2022 | Islamabad

## Slide 2: Shelter/NFI Sector Working Group
15.11.2022 Agenda
Welcome and Introduction (5Minutes)
5Ws updates(5Minutes)
Winterization (10Minutes)
Initial Brainstorming on recovery (10Minutes)
AOB

## Slide 3: 5W reporting
Two report process – pipeline or non pipeline
5W data quality:
  Ongoing activities
  People reached
Notes: A third of 5W entries are ongoing – doesn’t make sense in the emergency phase
One row is one distribution
Planned activities can’t have people reached
If you don’t report correctly you wont appear in the gap analysis - duplication

## Slide 4: 5Ws Data Presentation
  Link to consolidated 5Ws;
  https://docs.google.com/spreadsheets/d/1mPTxVhCtW-NHgAFtcScu9ptTKj99Ykm6y5-ObjBQ_DA/edit?usp=sharing
  Link to UNOCHA interactive dashboard
  2022 Monsoon 5W Dashboard | ReliefWeb Response
  Link to NFRCC dashboard
  nfrcc.nitb.gov.pk
Notes: National flood response and coordination center(NFRCC) .link is down, PM refuse to inaugurate
4

## Slide 5: Households Reached per Province
Balochistan
50,121
Gilgit Baltistan
1,650
Khyber Pakhtunkhwa
24,,656
Punjab
8,051
Sindh
152,356
20000
40000
60000
80000
100000
PROVINCE | HOUSEHOLDS REACHED
Sindh | 152,356
Balochistan | 50,121
Khyber Pakhtunkhwa | 24,656
Punjab | 8,051
Gilgit Baltistan | 1,650

## Slide 6
Gap per Province (households)
PROVINCE | GAP
Sindh | 436,331
Balochistan | 56,145
Khyber Pakhtunkhwa | met
Punjab | 17,147
Gilgit Baltistan | 503
*GAP is based against the target of 30% of all damaged and destroyed buildings (as per the revised flash appeal)
Balochistan
56,145
Gilgit Baltistan
503
Khyber Pakhtunkhwa
met
Punjab
17,147
Sindh
436,331
Gap (HHs) per Province
0
50000
100000
150000
200000
250000
300000
350000

## Slide 7: Sindh - Households Reached per District
Badin
2,125
Dadu
21,874
Ghotki
998
Hyderabad
2,580
Jacobabad
12,628
Jamshoro
2900
Kambar Shahdad Kot
17,475
Kashmore
7480
Khairpur
14,802
Larkana
1,140
Malir Karachi
2500
Matiari
620
Mirpur Khas
13,897
Naushahro Feroze
3,798
Sanghar
4292
Shaheed Benazir Abad
3957
Shikarpur
13,831
Sukkur
2989
Umer Kot
7951
2500
5000
7500
10000
12500
15000
17500
DISTRICT | HOUSEHOLDS REACHED
Dadu | 21,874
Shikarpur | 13,831
Kambar Shahdad Kot | 17,475
Jacobabad | 12,628
Mirpur Khas | 13,897
Umer Kot | 7,465
Kashmore | 6,252
Khairpur | 14,802
Sanghar | 4,106
Shaheed Benazir Abad | 3,550
Sukkur | 1,510
Jamshoro | 820
Malir Karachi | 2,500
Hyderabad | 2,580
Badin | 2,125
Qambar Shahdadkot | 17,475
Matiari | 1,331
Naushahro Feroze | 3,798
Larkana | 1,140
Ghotki | 998

## Slide 8: Gap per District (hh)
Badin
10287
Dadu
5512
Ghotki
4558
Hyderabad
-638
Jacobabad
13553
Jamshoro
11119
Kambar Shahdad Kot
-10792
Kashmore
28429
Khairpur
28796
Korangi Karachi
2.0
Larkana
67844
Malir Karachi
-2458
Matiari
2896
Mirpur Khas
46316
Naushahro Feroze
29660
Sanghar
-4292
Shaheed Benazir Abad
-3957
Shikarpur
-397
Sujawal
4236
Sukkur
-2989
Thatta
3009
Umer Kot
-7951
Sindh - Gap (HHs) per District
0
10000
20000
30000
40000
50000
60000
DISTRICT | GAP
Larkana | 67,844
Kamber | 65,534
Mirpur Khas | 46,316
SBA | 41,881
Umerkot | 37,742
Naushahro Feroze | 29,660
Khairpur | 28,796
Kashmore | 28,429
Jacobabad | 13,553
Jamshoro | 11,119
Badin | 10,287
Tando Allahyar | 6,550
Dadu | 5,512
Ghotki | 4,558
Sujawal | 4,236
Thatta | 3,009
Matiari | 2,896
*GAP is based against the target of 30% of all damaged and destroyed buildings (as per the revised flash appeal)

## Slide 9
Sindh - Households Reached per Tehsil
0
1000
2000
3000
4000
5000
6000
… work in progress

## Slide 10
Winterization – response from partners
Organization Name | How many winter kits have been procured/are available? | What is the composition of the winter kits? | What the estimated value of the winter kits? | What is the status of the kits (e.g. in procurement/in stock/delivered)? | When are they going to be delivered? | Where are they going to be delivered? (timeline of distribution)
ACTED | 0 | 2 Fleece blankets (addition to E shelter Kit) | 3,500 | Procurement | 25-11-2022 | District Naseerabad, Osta Muhammad, Jaffarabad and Jhal Magsi in Balouchistan province
ACTED | 0 | Mattress, Quilt & Fleece Blanket (addition to E shelter Kit) | 15,260 | Procurement | 15-12-2022 | Winterization kit to the flood affected communities in District Sanghar in Sindh province
Penny Appeal | 445 | Attached as Annex | 19,965 | Delivered | NA | 1: Umerkot 2: Naushero Feroz 3: Dadu 4: Khairpur 5: Rajanpur
Penny Appeal | 155 | Attached as Annex | 19,965 | Procurement | NA | 1: Umerkot 2: Naushero Feroz 3: Dadu 4: Khairpur 5: Rajanpur
Protection & Human Right Organization (PHRO) | 100 | high thermal blankets, thermal sheets, and winter clothes | 20,000 | Delivered | 20 th October to 30th October | Khairpur Mir's (20th October to 30th October)
AMRDF | 500 | Clothing Sets / Shawls/Sleeping Mats/Plastic Mats/Blankets / Quilts/ | 10,500 | 1000 | waiting for funds | 20 Days if Kits received
Courage Development Foundation | 30 | Blanket Matters/Gada Shawl Ladies Khais Pillow Bed Sheets 1 pair of shoes | 7,000 | Delivered | 01-11-2022 | UC Kaich of District Dera Ismail Khan
Communitty Development Network (CDN )Warah | 0 | balnket , sweeter , caps , | 4,000 | Need Request of balnket Submitted to IOM | still Not Received | UC Hamal
Development & Empowerment Society (DES) | IOM is supposed to provide winter kits. DES Pakistan intends to distribute 30,000 winter kits to flood affectees | Blankets, warm clothes, bedding, jackets/sweaters and socks | 7,000 | Requested to IOM | Waiting for IOM response | Districs Naushero Feroze, Dadu and Jacobabad, Sindh (3 districts)
Gorakh Foundation Sindh | 200 | 02 Blankets per/family | 5,000 | 80% delivered | this week | UC-2 Johi, US Siyal Dad
Villagers Development Organization (VDO) | N/A | N/A | N/A | N/A | N/A | N/A

## Slide 11
Winterization – response from partners

## Slide 12: Authorities Updates (SINDH)
PDMA prioritized 19 Districts on basis of Damages and Losses.
In South Sindh 9 Districts prioritized for emergency assistance and relief activities while in North Sindh 10 Districts prioritized.
Rapid Damage Assessment is ongoing in all notify Districts of Sindh will be complete till 15th November,2022.
Rapid Damage Assessment online Data is available ,will be share with all UN Agencies and other stake holders once completed and endorsed.
Tent cities has closed in all prioritized districts , just few relief camps still ongoing specially in those areas where still dewatering activities on going.

## Slide 13
Common pipeline partners reached over 88,900 families (600,000 individuals) with distribution of plastic sheets, ropes, kitchen sets, tent poles sets and/or shelter repair kits since the beginning of the flood emergency response.
Distributions took place in Sindh, Punjab and Balochistan provinces.
New partners registration is on hold at the moment due to large number of requests compared to the available stock.
The current pipeline stock is low at the moment. Therefore, very little number of applications will be approved in the coming few days due to limited stock availability. Requests targeting hard to reach areas will be prioritized.
To the moment there is no available funding to replenish the pipeline stock. Partners will be updated if the plans change.
Pipeline Updates

## Slide 14: Winterization

## Slide 15: SHELTER PRIORITIES FOR WINTERIZATION
  The key shelter priority is to keep the immediate space around bodies warm
  primarily by warm clothes and bedding. The key needs are for blankets
  secondary shelter priority is to provide protection from the elements, by providing a waterproof roof
  Ground insulation and bedding is key in preventing heat loss to the ground,.
  Providing thick quilts or high-quality blankets can provide personal insulation from the ground, whilst closed cell foam, or raised wooden floors will reduce this heat loss.
  Plastic sheeting is a key basic flooring component preventing rising damp
  To ensure a warm living environment, wind proofing is essential. Draughts can be blocked by plastic sheeting, canvas, or blankets over gaps.

## Slide 16: RECOMMENDED NFI KIT FOR FLOODS RESPONSE

## Slide 17: RECOMMENDED NFI KIT FOR FLOODS RESPONSE-Continu

## Slide 18: Winterized Shelter Technical Guidelines

## Slide 19: Winterized Shelter Technical Guidelines

## Slide 20: Kit for Winterization Upgrading of Tents

## Slide 21: Affected and prioritized districts
Damaged/destroyed houses

## Slide 22: Elevation

## Slide 23: Temperature (last winter)

## Slide 24
Temperature (last winter)

## Slide 25: PEOPLE REACHED
PRESENCE

## Slide 26: AoB